## WBS
License Management System — Work Breakdown Structure (WBS)
Task ID | Task Name | Layer | Priority | Implementation Steps | Tech Stack | Est. Days
PHASE 1: Database Schema & Key Generation Design
1.1 | Design Database Schema for License Tables | DB | Critical | 1. Create `licenses` table: id (UUID PK), key_hash (VARCHAR 64 UNIQUE), tier (ENUM), status (ENUM), customer_id (FK), max_devices, issued_at, activated_at, expired_at (TIMESTAMPTZ) 2. Create `license_activities` table: id, license_id (FK), event_type, actor_id, metadata (JSONB), created_at 3. Add composite index on (status, expired_at) for cron job efficiency 4. Write Flyway migration V1__create_license_tables.sql | PostgreSQL, Flyway, UUID | 2
1.2 | Implement Secure License Key Generation Algorithm | BE | Critical | 1. Generate raw key: UUID.randomUUID() + Base32(HMAC-SHA256(secret, timestamp + customerId)) 2. Store only SHA-256(raw_key) in DB, never plaintext 3. Inject signing secret via @Value from AWS Secrets Manager 4. Format as XXXX-XXXX-XXXX-XXXX for easy input 5. Unit tests for uniqueness and format (100% coverage) | Java 17, SHA-256, HMAC, Spring Boot | 2
PHASE 2: Backend — Core Logic & Validation
2.1 | API Create License (Admin) with Idempotency | BE/DB | Critical | 1. POST /api/admin/licenses — validate CreateLicenseRequest DTO 2. Call LicenseKeyGenerator, hash key, persist with status=PENDING 3. Write audit log (CREATED event) to license_activities 4. Return raw key once in response — never persisted server-side again 5. Secure endpoint with Spring Security: ADMIN role only | Spring Boot 3, Spring Security, JPA/Hibernate | 3
2.2 | API Activate License with Distributed Lock | BE | Critical | 1. POST /api/licenses/activate — receive raw key from client 2. Hash raw key → lookup DB by key_hash 3. Acquire Redis lock: SETNX lock:activate:{key_hash} {instanceId} EX 10 4. Inside lock: re-check status in DB (double-checked locking) 5. If PENDING: update activated_at, expired_at, status=ACTIVE 6. Write Redis cache: SET license:{key_hash} {json} EX {ttl_seconds} 7. Release lock; return 409 if lock fails, 400 if already activated | Redisson, Redis, Spring Boot, @Transactional | 4
2.3 | License Validation Interceptor / Filter | BE | Critical | 1. Implement LicenseValidationFilter extends OncePerRequestFilter 2. Extract license key from X-License-Key header 3. SHA-256 hash → Redis GET → deserialize LicenseCacheDto 4. Cache MISS: fallback query DB, repopulate Redis with remaining TTL 5. If status != ACTIVE: return 403 {error: LICENSE_INVALID, code: E4030} 6. Apply filter only to /api/v1/** — exclude /api/admin/** and /activate | Spring Security, Redis, OncePerRequestFilter | 3
2.4 | Background Cron Job — Expiration Reconciliation | BE | High | 1. @Scheduled(cron = "0 0 2 * * *") — runs 2 AM daily 2. Batch query: SELECT WHERE expired_at < NOW() AND status = 'ACTIVE' 3. Bulk update status=EXPIRED in batches of 500 4. DEL Redis keys for expired licenses (clock skew cleanup) 5. Publish expiry events for email notification (7-day warning) | Spring Scheduler, Redis, Spring Data JPA | 2
PHASE 3: Frontend — Admin Dashboard & Client Portal
3.1 | Admin Dashboard — License Lifecycle Management | FE | High | 1. Page /admin/licenses: DataTable with columns: Key (masked), Customer, Tier badge, Status chip, Dates, Actions 2. Create License Modal: tier select (3 options), DatePicker for custom expiry (Enterprise), Customer autocomplete 3. One-Time Key Dialog with copy button after creation 4. Filter bar: tier, status, date range — persist via URL search params 5. Bulk actions: Suspend / Revoke multiple licenses 6. License detail drawer: activity timeline, Extend Expiry button | Next.js 14, Shadcn/ui, TailwindCSS, React Query, TanStack Table | 5
3.2 | Client Activation Screen & Expiry Warning Banner | FE | High | 1. Page /activate: key input (auto-format XXXX-XXXX), submit, loading state 2. Success state: show tier, expiry date, unlocked features 3. Error states: INVALID_KEY (red), ALREADY_ACTIVATED (yellow), EXPIRED (red + renewal link) 4. Global Expiry Warning Banner: shows if < 7 days remaining 5. Persist banner dismiss state in localStorage | Next.js 14 App Router, Shadcn/ui, TailwindCSS, Zustand | 3
PHASE 4: Testing & Edge Cases
4.1 | Concurrency & Time-Travel Testing | BE | High | 1. Double activation test: 20 concurrent threads activate same key → only 1 succeeds, 19 get 409 2. Time-travel test: mock Clock bean → expired_at - 1s → expect 200; expired_at + 1s → expect 403 3. Redis TTL precision test: verify TTL set ±2s vs expired_at in DB 4. Cache miss fallback: flush Redis → call API → verify repopulate + 200 response 5. Cron reconciliation: inject records with expired_at=yesterday → run cron → assert status=EXPIRED | JUnit 5, Mockito, Testcontainers (Redis + PG), @MockBean Clock | 3
4.2 | Integration & Security Testing | BE/DevOps | Medium | 1. Full integration test: @SpringBootTest + Testcontainers — activate → DB → Redis end-to-end 2. Key brute-force test: verify SHA-256 makes enumeration infeasible 3. Role-based access: regular user cannot call admin endpoints (expect 403) 4. Load test: 1000 concurrent requests with valid license → Redis hit rate, P99 < 50ms | Testcontainers, Spring Security Test, JMeter / k6 | 3

## Summary
WBS Summary — License Management System
Phase | Tasks | Est. Days | Layer Coverage
Phase 1 — DB Schema & Key Gen | 2 | 4 | DB, BE
Phase 2 — Backend Core Logic | 4 | 12 | BE, DB
Phase 3 — Frontend | 2 | 8 | FE
Phase 4 — Testing | 2 | 6 | BE, DevOps
TOTAL | 10 | 30 | BE / FE / DB / DevOps